## Milestones
Feature List | Targets
All bugs and issues closed in POS | TODAY (50 K Line of code)
Testing of Reports Features
Testing of stock updation and addition
Testing of security screens
Purchase Modelling and Purchase Reports
Medicine Data Gathering through crawler
Milestone Completion of all wishlists and bugs for desktop POS | 1st September
Mobile End App for Pharmacy Client
Hospital end client and AbuSaad end Server software
Pharmaceutical company analytics
Pharmacy analytics
1st October

## RoadMap
Killer Features (Vow Features) | Entered By
What is the shortest path to next sale ?

## WishLists
No. | Basic Requirement | Sub-Requirement | Priority | Category | Complexity | Entered By
| User should be able to set expiry alarms for medicines in confirmation with different company requirements |  |  |  | Medium
| The front end layout should be configurable i.e., fonts etc for headers, ability to shown/hide columns |  |  |  | Low
Internationalization i.e., support for Urdu
Proper Installer for the application which installs jre as part of installation
Collection of sales analytics on the server end
| Ability to browse current stock |  |  | Feature
Price of items should be displayed along with the generics names so that salesman could make comparison of prices and recommend better medicine
Jar signing of class files
| Purchase reports are to be added |  | Critical
Cross-Platform support (for mobile phones)
Sale analytics for pharmacy
Instead of internet, orders should be placed through SMS
Button to be added for deleting medicines
Add X button to clear the elements in drop down list
Add + button to add the medcine to reciept
Change quantity and discount of medicine in table buttons should be added
When user moves the arrows over the table, medicine information e.g., stock expiry should be visible in bottom corner.
Features should be licensed individually
Download and include JFreeChart charts in reports
Customers data should be saved

## DesignChanges
Design Issues | Targets | Priority | Complexity
How to make the GUI resizable ? i.e., how to
How to have a plug-n-play licensing module i.e., licensing could be enabled or disabled without compromising security
How to avoid loading all of the sales receipt in a list ?
Design for internationalization
Code to be refactored to remove all global variables, so that making changes would be easier.
Separate dervied classes for each of the JInternalFrames
Each of the method in the code is to be enclosed in the try-catch block, traces should be printed and proper jlog errors should be printed for each exception. Class name and method name should be typed for each exception.
Ensuring the availability of an error log
Avoid global data and change accessors to private
Business logic in auto-complete box should be separated into a separate class or moved to mainframe class
Moving to JavaFX
There are queries for which we are using in-memory list, they should be change to direct queries from database.
Change technology so that database field change requires lesser code modification in database wrapper

## LookNFeel Test
Basics |  |  | Priority
Standard GUI Features
Tooltips on icons
Change basic icon of software
Print Receipt format
Headers for each dialog box with clear instructions for user
Icons for all operations including update stock and viewing reports
Ensure that user eyes don't get tired, i.e., visual elements on a screen are present on their expected locations
CLEAR and CANCEL button on reports on each form should be at the same location
All the tables for the reports should be visually aligned
All the tables within the software should have similar font for heading

## UnFixed_Issues_Bugs
Issue # | Screen | Description | Priority | Category | Complexity | Entered By
|  | When user scrolls the medicine drop down through mouse, he should be able to move up and down the list | Critical |  | High
|  | Layout doesn’t work for different screen sizes, it distorted for a larger screen size. Some forms are not full screen. | Emergency
|  | The precision of values shown in the total price text field should be set to a value. Its very long now exceeding bounds. | Critical
| Medicine Sales Report | Medicine Sales Report : Add button for displaying graph but it should be currently hidden.
| Medicine Sales Report | Medicine Sales Report : The medicine name field should be searchable.
| LOGIN Screen | Login dialog is displayed at top corner instead of middle |  | LookNFeel
Company name is not convert to lower case before storing in database. All entries to be converted to lower case before saving in database
| Receipt Screen | When multiple items are displayed in a drop down, we cannot scroll down to select a particular item | Emergency
| Receipt Screen | Total is not round-off to 2 digits | Medium
| Receipt Screen | There should be a button on the screen, saying that do you want to change quantity of selected item | Critical
| Total Company Sales | Distributor name and company name should be visible as drop down fields
| Total Returns by Medicine | Medicine name drop down box should be added here
| Total Returns by Salesman | Salesman name should be visible in a drop down box
| Overall Short Items | Items are displayed towards the bottom of the screen
| Overall Short Items | Current item quantity is not displayed in a column | Emergency
| Short Items by Company | Even if user enters the name of the company with a short medicine item, no medcine is displayed in the table | Emergency
| Short Items by Company | Black Border is displayed at bottom and a text box is cut from the right edge
| Short Items by Company | Medicine, Company and Distributor names should be available through drop-downs
| Short Items by Rack | When count exceeds a particular limit (10), the text gets hidden behind the arrow
| Short Items by Rack | Even if user selects a particular rack and specifies a very large no. from which all items quanity on that rack is lesser, none of the item is displayed in the table. | Emergency
| Remove User Group | Even when a group is removed by pressing the remove button, the group is not removed from the drop down
| Update Stock | For different categories of tablets and injections of even a single medicine, the user should not have to enter a medicine name multiple times. Facility to enter multilple information for a single medicine should be available on a single screen
| Update Stock | A same brand name could be manufactured by multiple vendors. This scenario should be catered, e.g., caltriol medicine
| Update Stock | Ability to specify type of medicine for e.g., suspension, injection, tablets etc.
| Add Stock | Test is to be added that expiry date must be later than manufacturing date. Other field checks should also be added
| Add Stock | When add stock screen is opened up, sometimes no check box is selected and items per pack box text box is disabled
| ALL SCREENS | Field validation checks and proper error messageshave to be added for each form
| Receipt Screen | User shouldn't have to press enter after selecting a medicine in drop down field
| Receipt Screen | The look and feel of main screen isn't good
Total print receipt width should be configurable from GUI and there should be facility for re-prints
Test if the total items in receipt are printed accurately even when we use the
User should be able to search from a list of generic medicines i.e., there should be two separate list/indexes for search 1. Medicines available in stock 2. Medicine available in the market
Form names should be visiable at the top
after entering a usergroup we have to restart software before we add users to the group
in add usergroup when we enter some user group its first alphabet apperas to be in small letter.
the total text box should be uneditable
when we select a medicine then we cant remove it from the textbox.
when we are giving overall discount to somebody then the particular amount which we want to deduct is not deducted from that total amount
in add stock medicine name textbox should not write numbers, same is the case with distributer name and company name
In process return when we write a receipt number and that number is not present in the database then it should have to show a dialog box that tell us that that record is not present
In reports when we are checking total sale of the medicine and name of medicine textbox should suggest the names of the medicine
In reports when we are checking total sale of company then we enter only distributor name and click on the show sales button then the dialogbox should warn that enter the company name and medicine name then total sale will be shown
In reports when we open total return by medicine, the text box of the medicine is samller as compared to others
Short Items by medicine : item count should not be allowed to go in negative or zero range
Help is missing from menu
Lisence should be strengthened

## Ahmad Assignments
No. | Assignment Description | Planned Hours | Actual Hours | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
| Add new gui for medicine addition according to distributor names |  |  | 10th August 2015 | 19th August 2015
| Internationalization |  |  | 20th August 2015 | 27th August 2015
| Graph addition in reports |  |  | 28th August 2015 | 10th September
| RND on medicine name drop down box improvements |  |  | 11th September 2015 | 21st September 2015
| Load testing and fixing load issues |  |  | 24th September 2015 | 31 September 2015

## Functionality Test
| Basics | Advanced | Test State
Testing Scenario # 1 (Use Case # 1 ) : | Return Receipts Usecase | ! Check stock updation | Pass/Fail
Testing Scenario # 2 (Use Case # 2 ) : | Printing accurate receipts Usecase
Testing Scenario # 3 (Use Case # 3) : | Reports are being shown accurately
Testing Scenari # 4 (Use Case # 4) : | Stock addition and updation are working as expected
Collection of sales data and performing analytics and selling the analytics
Security Testing
Testing sheets to be written for each feature
Note on C2: Pasha: - Place restriction on entry of multiple medicine names in table and then process return (i.e., remove one medicine) and press print receipt to find out why the receipt was not printed. -

## Usability Test
Icons are visible with tooltips
Help is accessible from each menu

## Performance Test
| Basics | Advanced
Testing Scenario # 1 (Use Case # 1 ) : | Test the performance of drop-down menu after adding 10,000 items.
Testing Scenario # 2 (Use Case # 2 ) :

## CompetitorAnalysis
Column1 | Column2 | Column3 | Column4
Main Feature | Sub Feature | AbuZar

## Customer_Feedbacks
Targets
Getting feedback from 100 Customers on this application
Do survey to prepare a list of bazars in lahore and medical stores without a software
Prepare a list of all pharmaceutical companies from pharma guide and their contact numbers. Prepare schedule to get updates about new products launched. Update product database based upon this information